## Slide 1: Innovation @ Brother
Digital
Innovation Hub
Opportunity Charter – Security Automation

## Slide 2
OPPORTUNITY | SAP Security Automation |  |  | 
BUSINESS FEASIBILITY |  | TECHNICAL FEASIBILITY |  | RECOMMENDED LOCATION
HIGH |  | HIGH |  | BIE - MIS
DESCRIPTION |  |  | ACTIVITY DETAIL | 
Using Robotic Process Automation, reduce or eliminate the manual effort required to perform standardised SAP Security tasks, where these meet certain criteria. Two SAP Security processes have been identified as highly likely to be suitable for automation. |  |  | 2 Initial use-case identified: Automation to Lock Inactive/dormant users (10 hours / month) Automation to Unlock Users and reset their Passwords (20 hours / month) Further detail on these process are shown on the following page. Reduction in manual effort means SDF staff can be redeployed onto alternative higher value work. | 
MVP IMPLEMENTATION ACTIVITIES |  |  | IMPLEMENTATION REQUIREMENTS, DEPENDENCIES & RISKS | 
Evaluate feasibility and viability: Viability Threshold - 0.25 FTE for desktop automation (WinAuto) Infrastructure requirements Process Documentation - Aligning documentation to automation standards WinAuto Development – 2-3 weeks for WinAuto including testing & QA Deploy and Monitor, including processes for exception management It may be possible to re-use previously developed robotic capability in some cases, reducing the time and cost to implement. |  |  | Automation SME – IBM India Automation Developer(s) – IBM India SDF SAP Team Security Process Documentation SDF SAP Team advising automation developer(s) Robot Hosting / Connectivity – Local Desktop or VDI RISK – Automation can be halted if exceptions cause pop-ups. To ensure smooth operation, the Robot will need to run on a machine which can be visually checked. If these exceptions occur out of hours, 24/7 operation will halt. | 
COST |  |  | BENEFIT | 
Estimated one-time Innovation Fund development cost: Development effort - £1,500 WinAuto Professional License - £750 Other One-time Costs – Infrastructure Requirements – Desktop or VDI hosting No regular Ongoing Charges expected Changes to SAP environment or other applications which impact the automation and require revisions will be charged at Flex rates, subject to prior agreement |  |  | Approx 0.2 FTE will be released to be deployed onto additional higher value work Equivalent of c.£8,550 at Flex Technical / Developer FTE (offshore) rate Reduced errors or ommisions / improved compliance with security policies | 

## Slide 3
Automation to Lock Inactive/dormant users
We are performing 30 days check (Manually done every month) to notify Superusers about inactive/Dormant account, based on provided report Superuser can take decision to retain/delete SAP accounts.
Actions to be taken to enable Automation –
If user is inactive in system, there should be an automated Email alert generated for user to log-on into system if access is required. Below are the recommended actions based on the inactivity time frame :-
Send notification to user if user is inactive in system since last 30 or 60 days.
Lock the user if user is inactive in system since 90 days.
Delete the user if user is inactive in system since 120 days.
This automation tool will be used 24/7.
SAP Security Automation Activity Description
As Is | To Be | Approx. Efforts Saved | Potential Additional Saving | System | Task Owners
Lock Inactive / Dormant Users (Monthly Manual Activity ) | 1. Automated Notifications to End Users for Inactivity 2. Automated Locking in case of no action post automated notification reminders for number of days | 10 hrs/month | SAP License Cost/user (Subject to License Terms) | ECC, BW, CRM, Hybris Marketing | SAP Security Team, Help Desk, SAP Governance Team (For APO, SEM systems)

## Slide 4
Automation to Unlock Users and reset their Passwords
SDF Team and Brother Help Desk both get large number of tickets to unlock SAP accounts and reset their passwords. With the help of this automation tool users can get their accounts unlocked and get the updated passwords in confidential mail.
Actions to be taken to enable Automation –
User needs to Input the information like Username, system for which they need their password to be reset.
Check if user is not locked, reset the password and send an Email to user with Updated Password.
Check if user is locked due to incorrect log-on, unlock the user and send an Email to user with Updated Password.
Check if user is locked by Administration, suggest user to contact Help desk.
This automation tool will be used 24/7.
SAP Security Automation Activity Description
As Is | To Be | Approx. Efforts Saved | Potential Additional Saving | System | Task Owners
User Account Unlock & Password Reset (JIRA Ticket Based) - Support available only during work hours | 1. Self Service Web Based portal to Unlock account and reset passwords 2. 24/7 Availability | 80 Tickets/month (Approx. 20 hrs/month) |  | ECC, BW, CRM, Hybris Marketing, APO, SEM | SAP Security Team, Help Desk, SAP Governance Team (For APO, SEM systems)

## Slide 5
SAP Security Automation – Outline Plan
 | Activity | D * | Owner | Days | Plan Start Date | Actual End Date | RAG (R / A / G / Complete) | Comments
UC1 - Phase – Planning, Set up and requirements |  |  |  |  |  |  |  | 
1 | User ID, environment |  | Dhanya, Anjali | 10 |  |  |  | Infrastructure approach to be determined
2 | PDD preparation |  | Anjali, Account SME | 5 |  |  |  | 
3 | AID Preparation, review and signoff | 2 | Dhanya, Account SME | 3 |  |  |  | 
4 | Dev review and prioritization | 1,2,3 | Dhanya, Dev team | 3 |  |  |  | 
5 | Process & Activity Walkthrough | 4 | Dev, Account SME | 1 |  |  |  | 
6 | Coding and Unit Testing | 5 | Dev team | 15 |  |  |  | 
7 | UAT, UAT Signoff | 6 | Dev team, Account SME | 4 |  |  |  | 
8 | Deployment | 7 | Dev team | 1 |  |  |  | 
9 | Hypercare | 8 | Dev team, Account SME | 10 |  |  |  | 
Other Activities |  |  |  |  |  |  |  | 
10 | WA Training nomination |  | Sai | 1 |  |  |  | If required
11 | WA Training |  | Anjali |  |  |  |  | If required
12 | Connectivity Details |  | Anjali | 1 |  |  |  | 
13 | Connectivity Test | 12 | Dhanya | 2 |  |  |  | 
* Dependency – Specify who / what dependency is on in the Owner column. Give current dependency status & actions in comments |  |  |  |  |  |  |  | 
Blockers and Issues |  |  |  | Help / Support / Decisions Needed |  |  |  |